## Sheet1
Enterprise Java, MadJavaTeamBeta Group Project Plan
Objective | Week | Journal Entry
Create a WebService to validate a user entered email. This would receieve as input, a String and return a boolean value via a WebService. |  | Just an initial suggestion. Other ideas? - Dave.
Administrative tasks and planning: | 2015-10-19 | Dave Sullivan - recruited team Beta: Eric Albee, Mitch Gundrum
Establish a Group, setup a repository, and share in git hub.
Create this plan document to help track tasks and discussion.
Place a few initial examples researched to share with team.
A sample using RegEx and Java wrapped as web services | 2015-10-26 | Eric put these into a repository to try with SoapUI. Mitch and Dave joined. Will test these and consider an additional use of the apache commons pre-built validator as a Web Service.
? | 2015-11-02
Present project | mm/dd/yyyy | TBD.